## Agreed Plan
Item No | objective | task | old task | old task id | owner | stakeholders | dependencies | RAG status | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01
Integrate sustainability into all procurement processes
1 | Integrate sustainability into all procurement processes | Completion of the sustainable procurement toolkit prioritisation methodology | Completion of the sustainable procurement toolkit prioritisation methodology | 1 | Procurement managers | Procurement Team | bar: 2020-02-01
2 |  | create list of sustainability criteria for standard procurement processes (specification setting and evaluation) - see SG Sustainability test spreadsheet | Sustainability Criteria Within Procurement Process (specification setting and evaluation) | 2 | Procurement leads | Procurement Team, Carbon Management Team | bar: 2020-02-01 to 2020-05-01
3 |  | Apply sustainability criteria to ongoing procurement processes | Identification of the prioritised commodities and services | 3 | Procurement Leads
4 |  | Apply sustainability criteria to Estates&Facilities professional services framework | Estates Professional Services – Option to join UIG | 9 | Cara Wright | Procurement Team, Estates & Facilities Team, Carbon Management Team | bar: 2020-07-01 to 2020-12-01
5 |  | Carbon Management team to select priority procurement areas to be involved in | This document seeks to confirm this | N/A | Carbon Management Team | Procurement Team | Item No 1 | bar: 2020-03-01 to 2020-04-01
6 |  | Balanced Scorecards/Supplier Management | Balanced Scorecards/Supplier Management | 23 | Contract Managers
Create SDS Disposals Policy
7 | Create SDS Disposals Policy | Initiation of Disposals Policy Working Group | Initiation of Disposals Policy Working Group (Owners Tom Wilson / Estates / Carbon Team / EIS) | 4 | Tom Wilson | bar: 2020-02-01 to 2020-03-01
8 |  | Identification of policy stakeholders |  | n/a | Tom Wilson | bar: 2020-03-01
9 |  | Writing of draft policy document |  | n/a | Tom Wilson | bar: 2020-04-01 to 2020-05-01
10 |  | Open editing of policy document by working group |  | n/a | Tom Wilson | bar: 2020-05-01 to 2020-07-01
11 |  | Approval seeking |  | n/a | Tom Wilson | bar: 2020-07-01 to 2020-08-01
12 |  | Publication of SDS Disposals Policy |  | n/a | Tom Wilson | Comms Team | bar: 2020-08-01 to 2020-09-01
reduce emissions of existing processes
13 | reduce emissions of existing processes | Review of stationery catalogue and creation of core item list | Existing contracts to be revised (stationery - environmental preferable products, core list / minimum order values) (Change responsible to Cara) | 5 | Cara Wright | bar: 2020-09-01 to 2020-11-01
14 |  | Usage and environmental impacts of new Azure hosting model compared to previous model - write report? | Azure Hosting – involvement with EIS in monitoring usage and improvements vs old hosting model (can forward contacts to meet with EIS and finance) | 10 | Carbon Management Team | Iain Skene, EIS | bar: 2020-05-01 to 2020-07-01
15 |  | Investigate how to improve rules based printing | Print – involvement in setting policy – particularly in improvements for rules based printing (can forward contacts within EIS) | 13 | EIS | Carbon Management Team | bar: 2020-05-01 to 2020-09-01
16 |  | Communicate new printing guidance to staff |  | n/a | EIS | bar: 2020-09-01 to 2020-10-01
17 | Digitisation of paper based processes | Identify areas where processes can be digitised | Digitisation of paper based processes | 19 | EIS (Ellen Ledingham) | bar: 2020-03-01 to 2020-06-01
create new SDS Procurement policy
18 | Create new SDS Procurement Policy | Create policy working group | New SDS Procurement Policy (merging RASP and Procurement Policy) | 15 | Tom Wilson | bar: 2021-01-01 to 2021-03-01
19 |  | Draft SDS procurement policy by merging old Procurement policy and RASP Policy |  | n/a | Tom Wilson | bar: 2021-02-01 to 2021-05-01
20 |  | Approval seeking |  | n/a | Tom Wilson | bar: 2021-06-01 to 2021-08-01
21 |  | Publication of new SDS Procurement Policy |  | n/a | Tom Wilson | Comms Team | bar: 2021-08-01 to 2021-09-01
Miscellaneous
22 | NTP’s – Option to join UIG |  |  | 8 | Carbon Management Team | bar: 2020-05-01 to 2020-06-01
23 | Sustainable Procurement Guidance - Why, What, When, Where | Demand Management Guidance - Why, What, When, Where | Sustainable Procurement Guidance - Why, What, When, Where | 28 | Tom Wilson | bar: 2020-03-01 to 2020-04-01
24 | Sustainable Procurement Lifecycle 5 Steps | Sustainable Procurement Lifecycle 5 Steps | Sustainable Procurement Lifecycle 5 Steps | 29 | Tom Wilson | bar: 2020-03-01 to 2020-04-01
25 | Sustainable Procurement Case Studies | Sustainable Procurement Case Studies | Sustainable Procurement Case Studies | 30 | Paul White | bar: 2020-03-01 to 2020-04-01
26 | Review of current carbon mgt reporting | Review that reporting methods are still appropriate |  | 17 | Carbon Management Team
27 | Sustainable Procurement Best Practice Guidance Note | Publish Best Practice Guidance Note |  |  | Iain Skene | bar: 2020-05-01 to 2020-07-01
28 | Sustainable Procurement Best Practice Academy Module | Publish Module on Academy |  |  | Iain Skene | bar: 2020-07-01 to 2020-10-01
29 |  | Updates to Procurement Connect Page to include Responsible & Sustainable Procurement Guidance |  |  | Iain Skene | bar: 2020-06-01
30 |  | Terms and Definitions of Sustainable Development / Procurement
Note on A27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: feel free to give this a different name/sort the below actions into different categories