## SDS QAP Exemplar 202526
Status | Who to action | Area(s) for improvement | Due date | Completion Date | Expected Impact | Actual Impact
In Progress | michael.mchugh@sds.co.uk | Although not a requirement for the frameworks offered, we do not currently include metaskills in our initial assessment of learners. | 2025-11-01 |  | A more robust evidence base for learner skills and knowledge at the initial assessment stage will further support planning of a tailored programme for each individual.
Not Started | karen.mcnutt@sds.co.uk | The range of partners we work with at present do not offer the specialist support that is required for apprentices with more complex support needs. | 2025-10-31 |  | The range of partners we work with will be increased and apprentices who have more complex additional needs will feel more supported throughout their qualification and their chances of success will be optimised.
In Progress | michael.mchugh@sds.co.uk | Participation rates of female apprentices on our Engineering programme is below the SDS national average. Participation rates of male apprentices on our Business Administration programme is below the SDS national average. | 2026-03-31 |  | 1) Increase female participation rate on the Engineering programme by 2% in 2025-26. 2) Increase the male participation rate on the Business Administration programme by 5% in 2025-26.
Not Started | karen.mcnutt@sds.co.uk | The response rate for our employer satisfaction survey is 45% which is below our internal target of 75%. Employer satisfaction levels were 88% last year which is below our internal target of 90%. | 2025-11-23 |  | Increasing the participation rate in the annual survey to a minimum of 75%. Employer satisfaction levels will increase and we will meet our internal target of 90%
`

## Tasks SDS QAP Exemplar 202526
Parent Area(s) for improvement | Task Title | Due date | Completion date | Who to action | Comments
Although not a requirement for the frameworks offered, we do not currently include metaskills in our initial assessment of learners. | plan and deliver a programme of staff CPD sessions to upskill delivery team on meta skills | 2025-06-01 |  | Michael McHugh
| Deliver a staff workshop to discuss options/ ideas for how metaskills might be incorporated into the initial assessment process | 2025-07-31 |  | Callum Rae
| Carry out pilot of new IA approach with a small group of learners and prepare a short report for management team outlining what worked well and where changes to process are required | 2025-09-30 |  | Karen McNutt
| Update the IA process to incorporate changes following the pilot and roll out to all learners | 2025-11-30 |  | Karen McNutt
The range of partners we work with at present do not offer the specialist support that is required for apprentices with more complex support needs. | Create database of current partner network and their service offer / areas of expertise | 2025-06-15 |  | Callum Rae
| Carry out mapping exercise of local organisations (using Google / Libraries / Community Outreach Team) to identify potential partners | 2025-08-30 |  | Karen McNutt
| Make contact with relevant organisations, set up initial meetings and establish key contacts / services and agree referral processes. | 2025-10-22 |  | Karen McNutt
| Update the partnership database with new partner details and share with delivery team. | 2025-10-13 |  | Callum Rae
Participation rates of female apprentices on our Engineering programme is below the SDS national average. Participation rates of male apprentices on our Business Administration programme is below the SDS national average. | Contact all local schools and make arrangements to attend next available careers sessions | 2025-09-30 |  | Michael McHugh | Already built contact database and plan to send email out to all schools on 1 September 2025
| Write at least 2 case studies (1 for each framework) re. diversity and post on our website | 2025-11-23 |  | Callum Rae
| Share good practice case studies with employer network to encourage more diverse recruitment | 2025-09-30 |  | Callum Rae
The response rate for our employer satisfaction survey is 45% which is below our internal target of 75%. Employer satisfaction levels were 88% last year which is below our internal target of 90%. | Assessors to speak with each of their employer contacts to highlight the survey and encourage completion, noting the benefits of providing feedback to improve quality of programme delivery | 2025-10-10 |  | Michael McHugh
| Carry out analysis of the 2024-25 employer survey and prepare a short report for management team to demonstrate comparison return rates and satisfaction rates for 2023-24 and 2024-25 employer surveys | 2025-11-30 |  | Callum Rae
| Playback feedback to our employers and actions taken via marketing comms in the form of 'You Said We Did' | 2026-01-31 |  | Callum Rae