## SDS QAP Exemplar 202627
Status | Who to action | Area(s) for improvement | Due date | Completion Date | Expected Impact | Actual Impact
In Progress | staff name | Processes for tracking and recording evidence of the development of meta skills are not consistent across all frameworks. | 2027-02-27 |  | Tracking of progress and recording of evidence of development of meta skills will be more robust and approaches will be consistent across all frameworks delivered.
Not Started | staff name | The range of partners we work with at present do not offer the specialist support that is required for apprentices with more complex support needs. | 2026-10-31 |  | The range of partners we work with will be increased and apprentices who have more complex additional needs will feel more supported throughout their qualification and their chances of success will be optimised.
In Progress | staff name | Participation rates of female apprentices on our Engineering programme is below the SDS national average. Participation rates of male apprentices on our Business Administration programme is below the SDS national average. | 2027-03-31 |  | 1) Increase female participation rate on the Engineering programme by 2% in 2026-27 2) Increase the male participation rate on the Business Administration programme by 5% in 2026-27
Not Started | staff name | The response rate for our employer satisfaction survey is 45% which is below our internal target of 75%. Employer satisfaction levels were 88% last year which is below our internal target of 90%. | 2026-11-30 |  | Increasing the participation rate in the annual survey to a minimum of 75%. Employer satisfaction levels will increase and we will meet our internal target of 90%
`

## Tasks SDS QAP Exemplar 202627
Area(s) for Improvement | Task Title | Due date | Completion date | Who to action | Comments
Processes for tracking and recording evidence of the development of meta skills are not consistent across all frameworks | Plan and deliver a workshop for all programme delivery staff to agree consistent and appropriate processes for tracking progress and recording evidence, using the SDS Guidance for Meta-skills delivery to inform discussions. | 2026-07-31 |  | staff name
| Carry out pilot of new IA approach with a small group of learners and prepare a short report for management team outlining what worked well and where changes to approaches are required | 2026-09-30 |  | staff name
| Evaluate success of new approaches to tracking and recording evidence, seeking feedback from staff and learners. | 2027-02-27 |  | staff name
The range of partners we work with at present do not offer the specialist support that is required for apprentices with more complex support needs. | Create database of current partner network and their service offer / areas of expertise | 2026-06-15 |  | staff name
| Carry out mapping exercise of local organisations (using Google / Libraries / Community Outreach Team) to identify potential partners | 2026-08-30 |  | staff name
| Make contact with relevant organisations, set up initial meetings and establish key contacts / services and agree referral processes. | 2026-10-22 |  | staff name
| Update the partnership database with new partner details and share with delivery team. | 2026-10-13 |  | staff name
Participation rates of female apprentices on our Engineering programme is below the SDS national average. Participation rates of male apprentices on our Business Administration programme is below the SDS national average. | Contact all local schools and make arrangements to attend next available careers sessions | 2026-09-30 |  | staff name | Already built contact database and plan to send email out to all schools on 1 September 2026
| Write at least 2 case studies (1 for each framework) re. diversity and post on our website | 2026-11-23 |  | staff name
| Share good practice case studies with employer network to encourage more diverse recruitment | 2026-09-30 |  | staff name
The response rate for our employer satisfaction survey is 45% which is below our internal target of 75%. Employer satisfaction levels were 88% last year which is below our internal target of 90%. | Assessors to speak with each of their employer contacts to highlight the survey and encourage completion, noting the benefits of providing feedback to improve quality of programme delivery | 2026-10-10 |  | staff name
| Carry out analysis of the 2025-26 employer survey and prepare a short report for management team to demonstrate comparison return rates and satisfaction rates for 2024-25 and 2025-26 employer surveys | 2026-11-10 |  | staff name
| Playback feedback to our employers and actions taken via marketing comms in the form of 'You Said We Did' | 2027-01-31 |  | staff name